## Intro
LHEES Delivery Support
Stakeholder Engagement Templates
Developed by Arup for Zero Waste Scotland
These templates are to assist with stakeholder engagement and should be used alongside the Stakeholder Engagement Framework.
They provide a structured layout to identify, map & analyse, plan and engage with stakeholders as part of the LHEES development.
The templates follow the below structure:
1. Identify the key stakeholders to engage in the LHEES
2. Analyse and Map stakeholders to understand their level of interest and influence in relation to LHEES and prioritise engagement
3. Plan key engagement activities across the LHEES process
4. Engage stakeholders, continuously monitoring and recording engagement, making updates as new stakeholders are identified
A copy of the Policy and Strategy Review Template (stakeholder tab) has also been provided for ease of access.
LHEES Guidance (page 21) on Stakeholder Mapping (Stage 1) - Local Heat And Energy Efficiency Strategies And Delivery Plans: Guidance (www.gov.scot)
Guidance on Stakeholder Mapping (LHEES)
Internal stakeholders that are to be responsible for the development and implementation of the LHEES Strategy and Delivery Plan should be identified to support internal governance and cross council coordination.
Internal stakeholders responsible for developing local plans, strategies and policy that relate to LHEES should be identified and mapped, with a view to reflecting these priorities in the framing of LHEES. Likewise, a similar exercise should be undertaken for any relevant external stakeholders.
For each LHEES Consideration relevant internal and external stakeholders should be identified and mapped, with a view to engaging and collaborating with them during the preparation and delivery of an LHEES.
The mapping exercise should consider: the level of influence and impact that the local authority has on the stakeholder and; the level of influence and impact the stakeholder has on fulfilling the ambitions of LHEES.
Key internal stakeholders should include: housing, planning, energy services, economic development, estates and community planning etc, as well as those that may be required to champion specific activity e.g. heat network development. Key external stakeholders should include: DNOs, Gas Distribution Networks (GDNs), NHS, Energy Saving Trust and Home Energy Scotland, registered social landlords, business groups, local communities and local community energy groups, existing heat network providers, producers of waste heat (e.g. industrial or energy production facilities) any delivery partners etc.

## 1. Identify
Stakeholder Identification Template
Identify stakeholders using the categories and examples in the tables below for guidance.
1. Internal and External stakeholders. Those internal and external to the local authority.
2. Primary and Secondary stakeholders. Primary – those that may be impacted, positively and negatively by LHEES e.g. communities, local authority employees, managers, delivery partners. Secondary – those that LHEES will not directly affect e.g. Trade bodies, local advocacy groups, internal officers competing for resource.
3. Direct and Indirect stakeholders. Direct – those that have the power and/or authority to influence and impact the direction of LHEES. Indirect – those that care more about the outcomes of LHEES rather than implementation and content.
Some stakeholder groups have already been populated under each category to aid identification - *** these are for example purposes only can be edited/removed as required ***
Once completed the stakeholders can be transferred to the Policy and Strategy Review Template, which captures further detail including:
Team, Service area (if applicable)
Named individual
Contact
LHEES Consideration focus
Interest (e.g. methodology, strategy, delivery)
Internal Stakeholders |  |  |  | External Stakeholders
Primary (directly impacted by LHEES) |  | Secondary (indirectly impacted by LHEES) |  | Primary (directly impacted by LHEES) |  | Secondary (indirectly impacted by LHEES)
Direct (can influence LHEES Strategy) | Indirect (Outcomes focused) | Direct (can influence LHEES Strategy) | Indirect (Outcomes focused) | Direct (can influence LHEES Strategy) | Indirect (Outcomes focused) | Direct (can influence LHEES Strategy) | Indirect (Outcomes focused)
Climate & Sustainability Services | Property & Estates | Building Standards | Economic/Business Development | Delivery Partners | Public sector estates | Business Groups | Interest Groups
|  |  |  | Utilities | Households | Land / Environment Agencies
Energy Services | Community Planning | Local Government Officials | Legal
|  |  |  | Heat network providers | Registered Social Landlords | Historic Buildings / Heritage Trusts
Planning & Housing |  | Environmental Health (e.g. Air Quality) | IT Systems
|  |  |  | Local waste heat producers | Housing Developers | Third / Voluntary Sectors
|  | Equalities Support | Finance
|  |  |  | Transport providers | Anchor Loads | Community Groups
Procurement
Cross-boundary Local Authorities

## 2. Map and Analyse - Internal
Stakeholder Mapping Template - Internal | [8 empty] | Do not remove
[9 empty] | Quadrants | 5 | 5
Add stakeholders to the 'Organisation' column under the relevant category. The 'Categories' can be added or edited as required. If more/less stakeholders are required than the slots available, insert/delete a new row within the table.
Fill out the details for each stakeholder, including relationship contact, relevant LHEES stages and considerations and level of involvement with LHEES.
Rank the Level of Interest (column H) and Level of Influence (column J) from 1-10, with 10 being the highest and 1 being the lowest. It is important that only the numerical score is input into these columns.
The Influence/Interest Matrix on the right hand side will automatically map the stakeholder based on the scoring.
Category | Organisation | Internal Contact | LHEES Stages 1 - Policy and Strategy Review 2 - Data and Tools Library 3 - Strategic Zoning and Pathways 4 - Generation of Initial Delivery Areas 5 - Building-level Pathway Assessment 6 - Finalisation of Delivery Areas 7 - LHEES Strategy 8 - LHEES Delivery Plan | LHEES Considerations 1 - Off Gas Buildings 2 - On Gas Buildings 3 - Heat Networks 4 - Poor Building Energy Efficiency 5 - Poor Building Energy Efficiency as driver of Fuel Poverty 6 - Mixed Use, Mixed Tenure and Historic Buildings | Detail on involvement with LHEES (to support stakeholder engagement planning) (e.g. methods+data, strategy, delivery, specific geographical areas or projects etc) | Level of interest the stakeholder has on fulfilling the ambitions of LHEES Score: (1-10) | Level of influence the stakeholder has on fulfilling the ambitions of LHEES Score: (1-10) | Additional notes/comments
Climate & Sustainability Services | Stakeholder 1 |  |  |  |  | 1 | 9
| Stakeholder 2 |  |  |  |  | 8 | 2
| Stakeholder 3 |  |  |  |  | 3 | 3
| Stakeholder 4 |  |  |  |  | 9 | 2
| Stakeholder 5 |  |  |  |  | 8 | 8
Energy Services | Stakeholder 6 |  |  |  |  | 3 | 6
| Stakeholder 7 |  |  |  |  | 5 | 4
| Stakeholder 8 |  |  |  |  | 2 | 2
| Stakeholder 9 |  |  |  |  | 10 | 7
| Stakeholder 10 |  |  |  |  | 3 | 6
Planning & Housing
Property & Estates
Community Planning
Building Standards
Local Government Officials
Environmental Health (e.g. Air Quality)
Equalities Support
Economic/Business Development
Legal
IT Systems
Finance
Procurement
Tier 2: Keep satisfied, meet needs
Tier 1: Key player, engage closely
Tier 3: Keep informed, show consideration
Tier 4: Least important, minimal effort

## 2. Map and Analyse - External
Stakeholder Mapping Template - External | [8 empty] | Do not remove
[9 empty] | Quadrants | 5 | 5
Add stakeholders to the 'Organisation' column under the relevant category. The 'Categories' can be added or edited as required. If more/less stakeholders are required than the slots available, insert/delete a new row within the table.
Fill out the details for each stakeholder, including relationship contact, relevant LHEES stages and considerations and level of involvement with LHEES.
Rank the Level of Interest (column H) and Level of Influence (column J) from 1-10, with 10 being the highest and 1 being the lowest. It is important that only the numerical score is input into these columns.
The Influence/Interest Matrix on the right hand side will automatically map the stakeholder based on the scoring.
Category | Organisation | Internal Relationship Holder | LHEES Stages 1 - Policy and Strategy Review 2 - Data and Tools Library 3 - Strategic Zoning and Pathways 4 - Generation of Initial Delivery Areas 5 - Building-level Pathway Assessment 6 - Finalisation of Delivery Areas 7 - LHEES Strategy 8 - LHEES Delivery Plan | LHEES Considerations 1 - Off Gas Buildings 2 - On Gas Buildings 3 - Heat Networks 4 - Poor Building Energy Efficiency 5 - Poor Building Energy Efficiency as driver of Fuel Poverty 6 - Mixed Use, Mixed Tenure and Historic Buildings | Detail on involvement with LHEES (to support stakeholder engagement planning) (e.g. methods+data, strategy, delivery, specific geographical areas or projects etc) | Level of interest the stakeholder has on fulfilling the ambitions of LHEES Score: (1-10) | Level of influence the stakeholder has on fulfilling the ambitions of LHEES Score: (1-10) | Additional notes/comments
Delivery Partners | Stakeholder 1 |  |  |  |  | 1 | 9
| Stakeholder 2 |  |  |  |  | 8 | 2
| Stakeholder 3 |  |  |  |  | 3 | 3
| Stakeholder 4 |  |  |  |  | 9 | 2
| Stakeholder 5 |  |  |  |  | 8 | 8
Utilities | Stakeholder 6 |  |  |  |  | 3 | 6
| Stakeholder 7 |  |  |  |  | 5 | 4
| Stakeholder 8 |  |  |  |  | 2 | 2
| Stakeholder 9 |  |  |  |  | 10 | 7
| Stakeholder 10 |  |  |  |  | 3 | 6
Heat network providers
Waste heat providers
Transport providers
Public Sector Estates
Households
Registered Social Landlords
Housing Developers
Business Groups
Land/Environment Agencies
Historic Buildings / Heritage Trusts
Third / Voluntary Sectors
Community Groups
Interest Groups
Cross-boundary LAs
Anchor Loads
Tier 2: Keep satisfied, meet needs
Tier 1: Key player, engage closely
Tier 3: Keep informed, show consideration
Tier 4: Least important, minimal effort

## 3. Plan
Stakeholder Engagement and Management Plan Template
The first template can be used to plan the key engagement activities for each LHEES Stage, and should be used for the overarching engagement plan. This has been pre-populated with some suggestions for each LHEES Stage, however these can be edited/updated as required.
The second template is provided to plan out specific engagement activities for a paticular stakeholder. This should be used for key (tier 1) stakeholders where engagement needs to be more closely monitored and outputs logged.
Engagement Plan by LHEES Stage: For main engagement activities at each LHEES Stage
| LHEES stage | Stage 1 | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 6 | Stage 7 & 8 | Stage 7 & 8 | Stage 7 & 8
| Activity date | Ongoing - March/April | Mid-April | Ongoing - March | Mid-April | Late-April | Late-June | Late-June to Early July | July | July
| Activity title | Stakeholder Mapping and Engagement Planning | Objective Setting | Data Collection | Baseline Feedback | Delivery Area Generation | Finalisation of Delivery Areas / Delivery actions | Consultation Strategy | Consultation Workshop | Consultation Period
| Stakeholders involved | Internal council stakeholders | Internal council and Tier 1 stakeholders | Council, RSL, DNO, EST, SGN etc | Council + identified stakeholders | Council + identified stakeholders | Council + identified stakeholders | Internal council | Council + identified stakeholders | Council + identified stakeholders + wider public
Engagement lead
| Type of engagement (e.g. meeting, workshop, one-to-one) | Workshop and meetings | Workshop | Meetings and Comms (via email) | Meetings | Workshop | Workshop | Meetings | Workshop | Online Awareness Session
| Purpose of engagement | Engage with the Council to identify, map and prioritise key stakeholders. | Knowledge building and awareness raising for key stakeholders; establishment of ongoing engagement opportunities and activities to support LHEES. | Collect and assemble key datasets required for the LHEES analysis. | Work closely with the Council to visualise baseline information. The output report should be engaging and compatible with the Councils IT system. Engage specifically on HN zoning, as per LHEES Guidance/Methodology. | Interactive workshop to explore and discuss initial Delivery Areas and recommendations alongside the wider policy, strategy and delivery environment. | Set out and ask for feedback on the finalised Delivery Areas (incorporating analysis to date). Explore key actions, enablers and challenges to support content for LHEES Strategy and Delivery Plan. | Develop communication strategy for the consultation process | Present the draft LHEES Strategy and Delivery Plan for discussion and feedback.​ | Awareness-raising and a Q&A session to support public consultation.
| Type of information required | List of stakeholders mapped to level of interest/influence | Policy and Strategy Review, LHEES considerations etc | HES data, local heat sources, building data etc | LHEES baselining tool and data | LHEES modelling outputs + scenarios | Delivery pathways from the optimisation modelling. | Draft LHEES Strategy and Delivery Plan Comms strategy | Draft LHEES Strategy and Delivery Plan | Draft LHEES Strategy and Delivery Plan - key consultation issues
| Output(s) | Mapping and categorisation of tiers of stakeholders that can be updated and referred to throughout the project – defining how these stakeholders will contribute to the development of LAEP and LHEES and what their interests are.​ Establishment of a project steering group.​ An engagement plan for key stakeholders, with stakeholder attendance mapped against defined activity.​ Specific focus groups e.g. RSLs / social housing and heat network development. ​ | Introduce LHEES (purpose, priorities, Considerations, delivery). ​ Drive further engagement and awareness for the stakeholders, framing this around key questions and knowledge requirements that each of them has. ​ Set out LHEES linkages to local policy and strategy ambitions​ Discuss and agree wider Priorities for LHEES (in addition to national ones).​ Ensure stakeholders understand the role they will play in the LHEES.​ Ongoing engagement plans, requests for data, delivery support etc. | Data uploaded (where possible) in accordance with the RFI and data handling lead.​ | A baseline report that has been reviewed by the Council and key stakeholders. | Delivery Areas to be taken forward for the purpose of more thorough building-level analysis (Stage 5) and delivery planning (Stages 6 and 8) | Finalisation of Delivery Areas, and within these, identifying potential projects and delivery activity. | A communication strategy that finalises who the Council will engage with, specifying the type and format of engagement. Provision of public consultation documents. | An updated draft LHEES Strategy and Delivery Plan (if required). | Recorded session for further use by the Council, if required.
Additional notes/comments
Engagement Plan by Stakeholder: For key stakeholders where engagement needs to be planned more closely
Stakeholder Details | Stakeholder
Assigned LA officer
Engagement tier (1/2/3/4)
Summary of stakeholder’s priorities, interest and expectations for LHEES
Frequency of engagement
Engagement Plan | Meeting date
LHEES stage (1-8)
Type of engagement (e.g. meeting, workshop, one-to-one)
Purpose of engagement
Outcomes
Actions
Additional notes/comments

## 4. Engage
Engagement Checklist
This checklist is from the LHEES methodology and can be used as a starting point to guide intial engagement sessions. This list be reviewed and updated with additional questions that are relevant/useful as stakeholder engagement is ongoing.
Seperate Workshop Facilitation Guidance has also been produced which provides a more detailed guide on how to plan and carry out initial engagement sessions with Tier 1/Tier 2 stakeholders.
Stakeholder Group | Discussion Points | Stakeholder 1 - Notes | Stakeholder 2 - Notes | Stakeholder 3 - Notes | Stakeholder 4 - Notes
Public Sector Estates | Key priorities, strategies and targets for the organisation
Existing and planned programmes of work
Opportunities for heat networks, including discussion of Potential Zones identified by the LHEES process and any interaction with existing networks
Key reports / documents / data (in relation to the above e.g. to understand the extent of existing heat networks, including which buildings are connected)
Electricity | Known areas of potential constraints and/or capacity (to support LHEES demand led approach)
Planned electricity network upgrades
Information sharing to feed LA plans into network investment plans
Indication of network upgrade requirements, depending on plans
Location of primary sub-stations (e.g. for waste heat sources)
Any DNO (SPEN or SSE) low carbon energy projects, pilots or feasibility studies?
DNOs strategic priority areas / focus in the short-, medium- and long-term – e.g. from RIIO-ED2
Key reports / documents / data (in relation to the above) from DNOs/LAs
LA to share plans of any new large scale deployment of low carbon technologies that will be connected to the electricity network
Gas | What areas of the local authority area are served and not served by the gas network? Properties on/off gas?
Are any parts of the network part of an independent network?
Understanding of the main gas consumers within the local authorities footprint – domestic/non-domestic/large or major gas consumers
Location of hydrogen pilots or feasibility studies
SGN’s strategic priority areas / focus in the short-, medium- and long-term, as well as the potential pathways for hydrogen
Hydrogen production – are you aware of any developments in the local authorities area?
Hydrogen storage - are you aware of any developments in the local authorities area?
If the local authority is considering the development of a hydrogen strategy for their region, how can the distribution of hydrogen through the gas network align with this?
Key reports / documents / data (in relation to the above)
Water and sewerage | Location of sewerage networks, and waste heat potential?
Possible to differentiate foul/stormwater/combined sewers in GIS?
Able to identify location of combined sewers greater than 300mm diameter?
Location of wastewater treatment plants, and waste heat potential?
Any Scottish Water low carbon energy projects, pilots or feasibility studies? E.g. use of water source heat pumps.
Key reports / documents / data (in relation to the above)
Registered Social Landlords | Key priorities, strategies and targets for the organisation
Existing and planned programmes of work
Key reports / documents / data (in relation to the above)
Community groups | Key community priorities and plans
Existing community led programmes of work
Heat network development | Key heat demands
(in relation to Potential Zones) | Existing heat networks - ownership and operation, connected buildings, current heat supply, decarbonisation targets and plans, appetite for expansion or proposed zone boundaries
Local Development Plan sites
Significant waste heat sources

## Policy_Strategy Review Template
Note: The following are example internal and external stakeholders that could be involved with a local authority's LHEES. The purpose of developing a list here is to allow the local authority to consider potential stakeholders involved with the Considerations and any local priorities outlined as part of the LHEES Strategy in a proactive manner to then build more detailed stakeholder maps for each LHEES Consideration. The below template also enables data holders to be identified and this information should support completion of the Data and Tools library in Stage 2. When the Delivery Plan is being developed for the LHEES, this stakeholder maps may be useful to cross-reference to frame actions around, updating as required.
Internal Stakeholders
Team | Service area (if applicable) | Named individual | Contact | LHEES Consideration focus | Interest e.g. Methodology, Strategy, Delivery
Housing (private)
Housing (Council)
Economic Development
Finance and Procurement
Estates
Planning
Social Care
Community Planning
Climate Change / Sustainability
Low Carbon Working Group
Climate Change Project Board
Member / Officer Working Group (tbc)
ICT
Add others here…
External Stakeholders
Organisation | Team area | Named individual | Contact | LHEES Consideration focus | Interest e.g. Methodology, Strategy, Delivery
Scottish Government | LHEES - Senior Policy Officer | Jamie Gregory | Jamie.Gregory@gov.scot
RSL
NHS
Health and Social Care Partnership
EST | HA & PEAT Data Manager
Delivery partner (e.g. SCARF)
HES
Utility network operators
Business groups
Third sector and voluntary sector
Community groups
Scottish Historic Buildings Trust |  |  | https://www.shbt.org.uk/
Society for Protection of Ancient Buildings Scotland |  |  | https://www.spab.org.uk/
The Architectural Heritage Society of Scotland |  |  | https://www.ahss.org.uk
Households
Add others here…